## Sheet1
App Name: Conversational Memory Bot – AI-Powered Photo Gallery Assistant
Developed by: Asrarul Hoque Eusha
Supervised by: Sarwar Miral & Nani Gopal Barai
Support by: Jishnu Sardar, Kenedy Sarkar
Sponsored by: BJIT Academy
# | Task Module | Features To be implemented | Activities to be done | App Dev (man-hours) | App Dev (man-Day) | Start Date | End Date | Module Total (man-month)
Week 1
1 | Project Initiation | 1.1 Project Definition | 1.1.1 Purpose and goals of the project | 1 | 0.125 | 25.02.03 | 25.02.03
|  |  | 1.1.2 Project scope and constraints | 1 | 0.125 | 25.02.03 | 25.02.03
|  | 1.2 Project Charter | 1.2.1 Project timeline | 2 | 0.25 | 25.02.03 | 25.02.03
|  |  | 1.2.2 Project resources | 2 | 0.25 | 25.02.03 | 25.02.03
|  |  | 1.2.3 Project risks and assumptions | 2 | 0.25 | 25.02.03 | 25.02.03
2 | Requirements Analysis | 2.1 Documenting Requirements | 2.1.1 Get requirements from trainers | 2 | 0.25 | 25.02.04 | 25.02.04
|  |  | 2.1.2 Validate and Analyze Requirements | 2 | 0.25 | 25.02.04 | 25.02.04
|  |  | 2.1.3 Prepare UML diagrams | 3 | 0.375 | 25.02.04 | 25.02.04
|  | 2.2 User Stories | 2.2.1 Create user stories | 3 | 0.375 | 25.02.04 | 25.02.05
|  |  | 2.2.2 Prioritize the user stories | 1 | 0.125 | 25.02.05 | 25.02.05
|  | 2.3 Prepare SRS | 2.3.1 Identify Functional Requirements | 2 | 0.25 | 25.02.05 | 25.02.05
|  |  | 2.3.2 Identify Non-Functional Requirements | 2 | 0.25 | 25.02.05 | 25.02.05
|  |  | 2.3.3 Project Scopes | 1 | 0.125 | 25.02.05 | 25.02.05
3 | Design | 3.1 User Interface Design | 3.1.1 Creation of wireframes for each page | 4 | 0.5 | 25.02.06 | 25.02.06
|  |  | 3.1.2 Design of user-friendly interface components | 2 | 0.25 | 25.02.06 | 25.02.06
|  | 3.2 ML Workflow & Database Design | 3.2.1 Design of metadata storage and indexing strategy for fast search | 1 | 0.125 | 25.02.06 | 25.02.06
|  |  | 3.2.2 Design the retrieval-augmented generation pipeline | 2 | 0.25 | 25.02.06 | 25.02.07
|  |  | 3.2.3 Determine steps for embedding extraction, search and indexing strategy | 1 | 0.125 | 25.02.07 | 25.02.07
|  |  | 3.2.4 Define the ranking mechanism and threshold distance | 1 | 0.125 | 25.02.07 | 25.02.07
|  | 3.3 Architecture Design | 3.3.1 Define high-level architecture of the application | 3 | 0.375 | 25.02.07 | 25.02.07
|  |  | 3.3.2 Design all application components and their interactions | 2 | 0.25 | 25.02.07 | 25.02.07
Week 2
4 | Development | 4.1 Front-End Development | 4.1.1 Design and implementation of HomePage | 4 | 0.5 | 25.02.10 | 25.02.10
|  |  | 4.1.2 Design and implementation of Gallery | 4 | 0.5 | 25.02.10 | 25.02.10
|  |  | 4.1.3 Design and implementation of Batch Image Uploader | 4 | 0.5 | 25.02.11 | 25.02.11
|  |  | 4.1.4 Design and implementation of Image Viewer | 4 | 0.5 | 25.02.11 | 25.02.11
|  |  | 4.1.5 Design and implementation of Chat | 4 | 0.5 | 25.02.12 | 25.02.12
|  | 4.2 ML Workflow Development | 4.2.1 Implementation of image feature extraction | 4 | 0.5 | 25.02.12 | 25.02.12
|  |  | 4.2.2 Implementation of image description generator and automatic tagging | 6 | 0.75 | 25.02.13 | 25.02.13
|  |  | 4.2.3 Implementation of text and image embeddings creation | 4 | 0.5 | 25.02.13 | 25.02.14
|  |  | 4.2.4 Implementation of NL query and vision similarity search | 6 | 0.75 | 25.02.14 | 25.02.14
Week 3
|  |  | 4.2.5 Implementation of contextual image retrieval model | 8 | 1 | 25.02.17 | 25.02.17
|  |  | 4.2.6 Implementation of relevance ranking | 8 | 1 | 25.02.18 | 25.02.18
|  | 4.3 Back-End Development | 4.3.1 Implementation of vector database | 2 | 0.25 | 25.02.19 | 25.02.19
|  |  | 4.3.2 Integration of vector database | 2 | 0.25 | 25.02.19 | 25.02.19
|  |  | 4.3.3 Implementation of API endpoints | 12 | 1.5 | 25.02.19 | 25.02.20
Week 4
|  |  | 4.3.4 Implement request validation and error handling | 4 | 0.5 | 25.02.24 | 25.02.24
|  |  | 4.3.5 Integration of API endpoints into the application | 4 | 0.5 | 25.02.24 | 25.02.24
|  |  | 4.3.6 Testing of API integration | 4 | 0.5 | 25.02.25 | 25.02.25
|  |  | 4.3.7 Code refactoring and Modularization | 4 | 0.5 | 25.02.25 | 25.02.25
|  |  | 4.3.8 Constant conversion and enum conversion of string | 4 | 0.5 | 25.02.26 | 25.02.26
5 | Testing | 5.1 Basic Acceptance Testing | 5.1 Test plan and test case development and case execution | 4 | 0.5 | 25.02.26 | 25.02.26
6 | Presentation | 6.1 Presentation Preparation | 6.1 Preparing Slides and revising SRS | 8 | 1 | 25.02.27 | 25.02.27
6 | Submission |  |  |  |  | 25.02.27 | 26.02.27